## Ideas
Requirements | MOSCOW | [14 empty] | Weeks
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Create interview | Should Have | bar: 1
Plan Interviews | Should Have | bar: 2
Interview relevant users | Should Have | bar: 2 to 3
Analyse interviews | Should Have | bar: 4
Create Use cases | Must Have | bar: 5
Collect Relevant data | Must Have | bar: 5 to 6
Normalise data | Must Have | bar: 6 to 7
ERD Diagram to manage homeless database | Must Have | bar: 7
Web Page Wireframe | Must Have | bar: 8 to 9
CSS to design web page | Must Have | bar: 10 to 11
HTML to design structure of web page | Must Have | bar: 14 to Weeks 15
Learn Node.Js for webpage | Must Have | bar: 14 to Weeks 15
XML file conversion | Must Have
Database connection | Must Have
Web Testing | Must Have | 2: strategic requirements analysis
Make front page | Must Have
Find palces for map | Must Have
Create Map | Must Have
Create Navigation bar | Must Have
Create Login | Could Have
Put website on hosting site | Must Have
Make front page | Must Have
Algorithm for checklists | Should Have
Create checklists page | Must Have
Add mobile

## Sheet 1
Sprint 1 | date |  |  |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Priotity | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Create Interview | 1.1 Create questions for interview | Must | 3 | 2 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5
| 1.2 Plan Interviews | Must | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
2. Contact charities | 1. Find relevant charities to interview | Must | 2 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3
| 2. Email relevant charities | Must | 2 | 0 | 0 | 1 | 2 | 1.5 | 0 | 0 | 0 | 0 | 0 | 4.5
3. Participate in interviews | 2.1 Conduct interviews using multiple charities | Must | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.2 Ask friends and families their takes on what could be introduced | Could | 3 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 5
4. Analyse Interviews | 3.1 See which information given is most relevant to the website | Must | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2
| 3.2 Decide which options are most important in order of priority | Must | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 2
| 3.3 Decide which features I would want to use for future updates | Should | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 2.5
Ideal - remaining work effort in Ideal hours |  |  | 17 | 15.3 | 13.6 | 11.9 | 10.2 | 8.5 | 6.8 | 5.1 | 3.4 | 1.7 | 3.1086e-15
Actual - remaining effort in Ideal hours |  |  | 17 | 15 | 12.5 | 8.5 | 4.5 | 0 | -3 | -3 | -5 | -8.5 | -8.5

## Sheet 2
Sprint 2 | date |  |  |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Priority | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Analyse Interviews | 1.1 Decide which features I want to add | Must | 0.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
2. Create Use Case | 1.3 Make scenarios | Must | 0.5 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3
| 1.3 Design Use cases | Must | 2 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 3
3.Create entity relationship diagram | 3.1 Identify tables required | Must | 3 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 3
| 3.2 Create relationships | Must | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0.5 | 0 | 1.5 | 4
| 3.3 Annotate Diagram | Should | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1.5 | 2
Ideal - remaining work effort in Ideal hours |  |  | 12 | 11.6 | 11.2 | 10.8 | 10.4 | 10 | 9.6 | 9.2 | 8.8 | 8.4 | 8
Actual - remaining effort in Ideal hours |  |  | 12 | 11 | 10 | 8 | 7 | 6 | 3 | 0 | -0.5 | -1 | -4

## Sheet 3
Sprint 3 | date |  |  |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Priotity | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Create web page wireframes | 1.1 Identify what How many pages I want and what I would like them to be | Must | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
| 1.2 Identify information needed for these pages | Must | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
| 1.3 Draw pages | Must | 5 | 0 | 0.5 | 0.5 | 2 | 0 | 3 | 1 | 0 | 0 | 0 | 7
2 Research similar websites | 2.1 Research colour schemes | Must | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 1 | 4
| 2.2 Research page layouts | Should | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 4
| 2.3 Research page design and information | Must | 4 | 0 | 0 | 0 | 2 | 0 | 1 | 1.5 | 0 | 0 | 1 | 5.5
Ideal - remaining work effort in Ideal hours |  |  | 19 | 17.1 | 15.2 | 13.3 | 11.4 | 9.5 | 7.6 | 5.7 | 3.8 | 1.9 | 0
Actual - remaining effort in Ideal hours |  |  | 19 | 15.5 | 13 | 12.5 | 10.5 | 9.5 | 5.5 | 3.5 | 0.5 | 0.5 | -1.5

## Sheet 4
Sprint 4 | date |  |  |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Priority | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1.Setup coding software | 2.1 research relevant software and hardware needed | Must | 2 | 2 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 5.5
| 2.2 Download and install anything required | Must | 0.5 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 2
| 2.3 Ask for reccomendations | Could | 1 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0.5
| 2.4 Find w |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. Create database | 3.1 Create database in PhpMyAdmin | Must | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 3.2 Gather Data | Must | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3
| 3.3 Populate Database | Must | 2 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 1.5
3. Connect Database | 3.1 Connect Database to website | Must | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 1 | 6
4. Testing | 4.1 Test database Connection | Must | [7 empty] | 1 | 0.5 | 2
Ideal - remaining work effort in Ideal hours |  |  | 11.5 | 10.35 | 9.2 | 8.05 | 6.9 | 5.75 | 4.6 | 3.45 | 2.3 | 1.15 | -1.7764e-15
Actual - remaining effort in Ideal hours |  |  | 11.5 | 9.5 | 7.5 | 7 | 5 | 1.5 | 0.5 | -2 | -3 | -6.5 | -9

## Sheet 5
Sprint 5 | date |  |  |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Priotity | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Navbar work | 1.1 Research other nav bar designs | Must | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 1.2 Create Navbar design | Must | 3 | 0 | 0 | 0 | 0.5 | 1 | 0 | 0 | 0 | 0 | 0 | 1.5
| 1.3 Add CSS for Nav bar | Must | 2 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.5
2. Create Front page | 2.1 Design front page layout | Must | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 2.1 Code CSS for Front page | Must | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 Add UX improvements | Could | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. Create Login | 3.1 Add login and register buttons to nav bar | Must | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5
| 3.2 Create login and register forms attachted to button | Must | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. Testing | 4.1 Test functionality of links | Must | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
| 4.2 Test page resize | Must | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4.3 Test Login | Could | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4.4 Test Buttons | Must | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal - remaining work effort in Ideal hours |  |  | 26.5 | 23.85 | 21.2 | 18.55 | 15.9 | 13.25 | 10.6 | 7.95 | 5.3 | 2.65 | 0
Actual - remaining effort in Ideal hours |  |  | 26.5 | 26.5 | 26.5 | 25.5 | 25 | 23.5 | 23.5 | 23.5 | 23.5 | 22 | 21

## Sheet 6
Sprint 6 | date |  |  |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Priotity | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Navbar Work | 1.1 Create Navbar Design | Must | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
| 1.2 Add CSS for Navbar | Must | 0 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.5
2. Create Front Page | 2.1 Design front page layout | Must | 2 | 0 | 1 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3.5
| 2.1 Code CSS for Front page | Must | 2 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 5
| 2.3 Add UX improvements | Could | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 Create login and register forms attachted to button | Must | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 4
3. Testing | 3.1 Test functionality of links | Must | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
| 3.2 Test page resize | Must | 2 | 0 | 0 | 0.5 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 2
| 3.3 Test Login | Must | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 3.4 Test Buttons | Must | 0.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Ideal - remaining work effort in Ideal hours |  |  | 21.5 | 19.35 | 17.2 | 15.05 | 12.9 | 10.75 | 8.6 | 6.45 | 4.3 | 2.15 | 0
Actual - remaining effort in Ideal hours |  |  | 21.5 | 16.5 | 12 | 9 | 9 | 6 | 4 | 2.5 | 2.5 | -0.5 | -2.5

## Sheet 7
Sprint 7 | date |  |  |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Priotity | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Code for maps | 1.2 Learn to code for maps | Must | 5 | 3 | 0 | 0 | 2 | 1.5 | 0 | 0 | 0 | 2 | 0 | 8.5
| 1.3 Implement what ive learnt | Must | 15 | 1 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 2.5 | 0 | 7.5
2. Code for database | 1.1 Learn to code for database connection | Must | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 3
| 1.2 implement what ive learnt | Must | 2 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2.5
3. Add excess functionality | 3.1 Make the website mobile friendly | Could | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2 Add the ability to show distance from location | Could | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Add the function to click two or more types to get a narrowed search | Should | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2 Introduce designs ideas from other websites | Could | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. Testing | 3.1 Test Map page | Must | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2 Test Database connection | Must | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Test Databsebase output of information | Must | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal - remaining work effort in Ideal hours |  |  | 67 | 60.3 | 53.6 | 46.9 | 40.2 | 33.5 | 26.8 | 20.1 | 13.4 | 6.7 | -1.2434e-14
Actual - remaining effort in Ideal hours |  |  | 67 | 63 | 63 | 60.5 | 55.5 | 53 | 53 | 53 | 50 | 45.5 | 45.5

## Sheet 8
Sprint 8 | date |  |  |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Priotity | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Code for maps | 1.1 Learn to code for maps | Must | 6 | 0 | 2.5 | 0 | 0 | 1 | 1.5 | 0 | 0 | 0 | 0 | 5
| 1.2 Implement what I have learnt | Must | 15 | 2 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 6
2. Code for database | 1.1 Learn to code for maps | Must | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1.2 Implement what I have learnt | Must | 2 | 1.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5
3. Add excess functionality | 3.1 Make the website mobile friendly | Could | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2 Add the ability to show distance from location | Could | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Add the function to click two or more types to get a narrowed search | Should | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2 Introduce designs ideas from other websites | Could | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. Testing | 3.1 Test each web pages functionality | Must | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2 Test mobile functionality | Could | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal - remaining work effort in Ideal hours |  |  | 67 | 60.3 | 53.6 | 46.9 | 40.2 | 33.5 | 26.8 | 20.1 | 13.4 | 6.7 | -1.2434e-14
Actual - remaining effort in Ideal hours |  |  | 67 | 62.5 | 57 | 57 | 57 | 54 | 50.5 | 50.5 | 50.5 | 50.5 | 50.5

## Sheet 9
Sprint 9 | date |  |  |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Priotity | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Code for Maps | 1.1 Learn to code | Must | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 Implement what I have learnt | Must | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. Add excess functionality | 3.1 Make the website mobile friendly | Could | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2 Add the ability to show distance from location | Could | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Add the function to click two or more types to get a narrowed search | Should | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2 Introduce designs ideas from other websites | Could | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. Testing | 3.1 Test each web pages functionality | Must | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2 Test mobile functionality | Could | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal - remaining work effort in Ideal hours |  |  | 62 | 55.8 | 49.6 | 43.4 | 37.2 | 31 | 24.8 | 18.6 | 12.4 | 6.2 | -8.8818e-15
Actual - remaining effort in Ideal hours |  |  | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62

## Sheet 10
Sprint 10 | date |  |  |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Priotity | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Code for maps | 1.1 Learn Code for maps | Must | 6 | 1.5 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5
| 1.2 Implement what I had learnt | Must | 15 | 3 | 0 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 6
2. Upload webpage to hosting site | 1.1 Decide which files are needed | Must | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 3
| 2.2 Upload files | Must | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 Correct file paths | Must | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. Add excess functionality | 3.1 Make the website mobile friendly | Could | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2 Add the ability to show distance from location | Could | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Add the function to click two or more types to get a narrowed search | Should | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2 Introduce designs ideas from other websites | Could | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. Testing | 3.1 Test maps functionality | Must | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2 Test Webpage hosting site connection | Must | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 1
| 3.3 Test mobile functionality | Could | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal - remaining work effort in Ideal hours |  |  | 70 | 63 | 56 | 49 | 42 | 35 | 28 | 21 | 14 | 7 | 0
Actual - remaining effort in Ideal hours |  |  | 70 | 65.5 | 64.5 | 62 | 60.5 | 60.5 | 60.5 | 60.5 | 58 | 56.5 | 56.5

## Sheet 11
Sprint 11 | date |  |  |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Priority | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Upload webpage to hosting site | 1.2 Upload and manage files | Must | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
| 1.3 Correct File paths | Must | 2 | 0 | 1 | 2 | 1.5 | 0 | 0 | 0 | 1.5 | 2 | 3 | 11
2. Add additional pages | 1.2 Design page in HTML | Should | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 make CSS for page | Should | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. Add excess functionality | 3.1 Make the website mobile friendly | Could | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2 Add the ability to show distance from location | Could | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Add the function to click two or more types to get a narrowed search | Should | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2 Introduce designs ideas from other websites | Could | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. Testing | 3.1 Test each web pages functionality | Must | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2 Test mobile functionality | Could | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal - remaining work effort in Ideal hours |  |  | 65 | 58.5 | 52 | 45.5 | 39 | 32.5 | 26 | 19.5 | 13 | 6.5 | 0
Actual - remaining effort in Ideal hours |  |  | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65

## Sheet 12
Sprint 12 | date |  |  |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Priotity | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Upload website to hosting site | 1.1 Reupload webpage | Must | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 3.5
| 1.2 Fix Paths | Must | 2 | 1 | 0.5 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 4.5
2. Add additional pages. | 1.1 Gather web page ideas | Should | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
| 1.2 Design page in HTML | Should | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 1 | 5
| 1.3 make CSS for page | Should | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 1 | 4
3. Add excess functionality | 3.1 Make the website mobile friendly | Could | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2 Add the ability to show distance from location | Could | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Add the function to click two or more types to get a narrowed search | Should | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2 Introduce designs ideas from other websites | Could | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. Testing | 3.1 Test gmaps pages functionality | Must | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 1.5 | 4.5
| 3.2 Test mobile functionality | Could | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Test website upload | Must | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal - remaining work effort in Ideal hours |  |  | 71 | 63.9 | 56.8 | 49.7 | 42.6 | 35.5 | 28.4 | 21.3 | 14.2 | 7.1 | -8.8818e-15
Actual - remaining effort in Ideal hours |  |  | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 67 | 63 | 60 | 56.5

## Sheet 13
Sprint 1 | date |  |  |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Priority | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Remake maps page | 1. Fix maps connection with xml File | Must | 5 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 3
| 2. Fix maps page design | Must | 7 | 0.5 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 5.5
2. Upload Web page | 1.1 Uploading Files | Must | 4 | 2 | 1 | 0 | 0 | 0 | 3.5 | 1.5 | 0 | 0 | 0 | 8
| 1.2 Correcting Paths | Must | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2
3. Add excess functionality | 3.1 Make the website mobile friendly | Could | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2 Add the ability to show distance from location | Could | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Add the function to click two or more types to get a narrowed search | Should | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2 Introduce designs ideas from other websites | Could | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. Testing | 4.1 Test Maps Page | Must | 2 | 2 | 1 | 0 | 0 | 0 | 2 | 0.5 | 0.5 | 0 | 0 | 6
| 4.2 Test webpage upload | Must | 2 | 0 | 1.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5
Ideal - remaining work effort in Ideal hours |  |  | 42 | 37.8 | 33.6 | 29.4 | 25.2 | 21 | 16.8 | 12.6 | 8.4 | 4.2 | 0
Actual - remaining effort in Ideal hours |  |  | 42 | 39 | 38 | 38 | 38 | 38 | 34.5 | 33 | 33 | 33 | 32

## Sheet 14
Sprint 1 | date |  |  |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Priority | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Google maps page | 1. Fix maps connection with xml File | Must | 4 | 2.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5
| 2. Add algorithm for output | Should | 5 | 0 | 1.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5
2. Add additional pages. | 1.1 Gather web page ideas | Must | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 Design page in HTML | Must | 15 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
| 1.3 make CSS for page | Should | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. Add excess functionality | 3.1 Make the website mobile friendly | Could | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2 Add the ability to show distance from location | Could | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Add the function to click two or more types to get a narrowed search | Should | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2 Introduce designs ideas from other websites | Could | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. Testing | 3.1 Test maps pages functionality | Must | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
| 3.2 Test mobile functionality | Could | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 2
| 3.3 Test Functionality of login | Must | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal - remaining work effort in Ideal hours |  |  | 72 | 64.8 | 57.6 | 50.4 | 43.2 | 36 | 28.8 | 21.6 | 14.4 | 7.2 | -1.2434e-14
Actual - remaining effort in Ideal hours |  |  | 72 | 69 | 67 | 66 | 65 | 65 | 65 | 64 | 64 | 64 | 64